## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Project | Rare Book Inventory & Sales Ecosystem (RISE)
| Detailed Oriented Tester | Robert Yribia
| Logic Architect (Backend Developer) | Midori (Alyssa Brown)
| Scrum Master | Vincent De Guzman
| UI/UX (Frontend Developer) | James Mather
| Lead Developer | Lyiondra Bradley
| Business Analyst | Gustavo Rosas
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
Story-01 | Inventory Management Dashboard | As a Librarian, I want to view and manage books in a table so that I can track the store’s rare collection digitally. | 1. Masked passwords. 2. Redirect to dashboard. | 1 | 1 | Alyssa/James
Story-04 | Data Validation & Security | As the Architect, I want to enforce ISBN and Price formatting so that the database remains clean and searchable. | 1. ISBN field rejects non-numeric characters. 2. Price field enforces two decimal places. 3. Form displays error if ISBN is not 10 or 13 digits. | 1 | 1 | Lyiondra/Robert
RISE-005 | Secure API & DB Handshake (Atlas) | Establish a secure, live connection between the Node.js server and the MongoDB Atlas cloud cluster. | 1. Successful connection log in console. 2. Auth error handling for incorrect credentials. 3. Data persists in Atlas cluster. | 1 | 1 | Lyiondra Bradley
RISE-002 | Add New Book Logic & Mock Data | Implementation of the backend logic to insert book records and seeding the DB with a 10-item initial census. | 1. Logic handles JSON payloads. 2. 10 mock items successfully uploaded to cloud. 3. Return 201 Created on success. | 1 | 1 | Lyiondra
ENV-101 | Environment Variable Config (.env) | Security task to mask sensitive database credentials and API keys using a .env file and dotenv package. | 1. .env file created and added to .gitignore. 2. Credentials accessed via process.env. 3. No plain-text keys in code. | 1 | 1 | Lyiondra
RISE-001 | User Login Interface Setup | Development of the frontend login screen and initial connection logic to the authentication backend. | 1. Input masking for passwords. 2. Form validation for empty fields. 3. Redirection logic upon successful login. | 1 | 1 | Alyssa/Lyiondra
RISE-003 | Initial Inventory Schema Design | Definition of the data structure for rare books, including fields for provenance, edition, and condition. | 1. Schema supports ISBN-10 and ISBN-13. 2. Enforced data types for Price (Number) and Date. 3. Documented in design folder. | 1 | 1 | James/Lyiondra
Story-02 | POS Checkout Interface | As a Sales Associate, I want to add items to a cart and see a subtotal so that I can process customer purchases. | 1. Selected items appear in the "Cart" area. 2. System calculates 7% tax automatically. 3. "Checkout" clears the cart and resets total. | 2 | 1 | Alyssa
Story-03 | User Authentication Prototype | As a Store Manager, I want a functional login prototype so that I can verify only staff can access the inventory | 1. UI switches to Dashboard upon "Login". 2. Visual feedback for incorrect password. 3. Form prevents empty submissions. | 3 | 1 | James
PER-201 | Index Author/Title (Search) | Performance optimization to index database fields to ensure search results return in under 2 seconds. | 1. Database indices created for 'author' and 'title'. 2. Query performance tested with 100+ records. | 2 | 2 | James
RISE-004 | Cloudinary Integration | Integration of Cloudinary API to host high-resolution book images without slowing down the primary database. | 1. Image upload limit set to 5MB. 2. URLs stored in the database. 3. Successful image rendering in Dashboard. | 2 | 2 | Lyiondra

## Sprint 1
T1-01
Sprint #1Tracking Sheet
|  | Project |  |  | Rare Book Inventory & Sales Ecosystem (RISE)
|  | Sprint # |  |  | 1
|  | Start date |  |  | 2026-03-25
|  |  | Total Team Members |  | 1900-01-04
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Status | Initial estimate | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07
T1-01 | Story-01 | Design HTML/Bootstrap layout for Inventory Table | James Mather | Complete | 4
T1-02 | Story-01 | Script JavaScript logic for 'Add Book and Delete' | Alyssa Brown | Complete | 8
T1-03 | Story-01 | Implement LocalStorage persistence for books | Alyssa Brown | Complete | 4
T1-04 | Story-03 | Create Login Form and validation logic | James Mather | Complete | 6
T1-05 | Story-04 | Create RegEx Patterns for ISBN and Price validation | Robert Yribia | Complete | 4
T1-06 | Story-02 | Build POS Checkout Interface and subtotal logic | Alyssa Brown | Complete | 10
T1-07 | Story-04 | Secure API & Database Handshake (Atlas) | Lyiondra Bradley | Complete | 8
T1-08 | Story-04 | Environment Variable Configuration (.env) | Lyiondra Bradley | Complete | 2
T1-09 | Story-01 | Add New Book Logic & Mock Data Insertion | Lyiondra Bradley | Complete | 4
T1-10 | Story-04 | Initial Inventory Schema Design | Lyiondra Bradley | Complete | 3
T1-11 | Story-03 | User Login Interface Setup (Frontend/Backend link) | Alyssa / Lyiondra | Complete | 4
|  | Remaining units (actual) |  |  | 80 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  |  | 74.2857 | 68.5714 | 62.8571 | 57.1429 | 51.4286 | 45.7143 | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | 0
[11 empty] | 0 | 57 | [5 empty] | 0 | 0
[11 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  |  | RISE (Rare Book Inventory & Sales Ecosystem)
|  | Sprint # |  |  | 2
|  | Start date |  |  | 2026-04-03
|  |  | Total Team Members |  | 5
[7 empty] | week 1 | [6 empty] | week 2
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Status | Initial estimate | Priority | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16
T2-01 | Story-05 | Design Kanban board UI for procurement | Gustavo Rosas | In Progress | 4 | 2
T2-02 | Story-05 | Implement status-tagging (Ordered/Shipped) | Alyssa Brown | In Progress | 8 | 2
T2-03 | Story-06 | Script 15-minute inactivity timer & redirect | Alyssa Brown | In Progress | 4 | 1
T2-04 | Story-06 | Test session timeout across browsers | Robert Yribia | In Progress | 6 | 1
T2-05 | Story-07 | Index Author/Title for <2s Search | Lyiondra | In Progress | 4 | 2
T2-06 | Story-08 | Cloudinary API Integration (Image Hosting) | Lyiondra Bradley | In Progress | 10 | 2
Story-05
Story-06
Story-07 | Story-01
Story-08
|  | Remaining units (actual) |  |  | 80 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  |  |  | 74.2857 | 68.5714 | 62.8571 | 57.1429 | 51.4286 | 45.7143 | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | 0
[12 empty] | 0 | 36 | [5 empty] | 0 | 0
[12 empty] | 10 | 0 | [5 empty] | 10 | 0